## Sheet1
Area Path | Assigned To | Business Value | Changed Date | Closed Date | Created Date | Cycle Time Days | Data Fim Previsto | Data Início Previsto | Effort | Iteration End Date | Iteration Path | Iteration Start Date | Lead Time Days | Priority | Project Name | Service Now | Tags | Title | State | Value Area | Versão | Work Item Id | Work Item Type
Teste Analytics | Ísis Monteiro | 128 | 2023-01-16 | 2023-01-16 | 2023-01-02 | 14 | 2023-01-16 | 2023-01-02 | 15 | 2023-01-16 | Teste Analytics/Sprint 1 | 2023-01-02 | 14 | 3 - Baixa | Projeto 2 | Projeto1 |  | Backlog 1 | Concluído | Business | 1.0 | 4200 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 179 | 2023-01-16 | 2023-01-16 | 2023-01-02 | 14 | 2023-01-16 | 2023-01-02 | 9 | 2023-01-16 | Dev. Analytics/Sprint 1 | 2023-01-02 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Backlog 2 | Concluído | Business | 1.0 | 4201 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 120 | 2023-01-16 | 2023-01-16 | 2023-01-02 | 14 | 2023-01-16 | 2023-01-02 | 38 | 2023-01-16 | Teste Analytics/Sprint 1 | 2023-01-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Backlog 3 | Em homologação | Business | 1.0 | 4202 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 169 | 2023-01-16 | 2023-01-16 | 2023-01-02 | 14 | 2023-01-16 | 2023-01-02 | 26 | 2023-01-16 | Análise de Requisitos/Sprint 1 | 2023-01-02 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Backlog 4 | Concluído | Business | 1.0 | 4203 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 105 | 2023-01-31 | 2023-01-31 | 2023-01-17 | 14 | 2023-01-31 | 2023-01-17 | 12 | 2023-01-31 | Análise de Requisitos/Sprint 2 | 2023-01-17 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Backlog 5 | Em homologação | Business | 1.0 | 4204 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 141 | 2023-03-17 | 2023-03-17 | 2023-02-01 | 44 | 2023-02-15 | 2023-02-01 | 21 | 2023-02-15 | Teste Analytics/Sprint 3 | 2023-02-01 | 44 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 6 | Concluído | Business | 1.0 | 4205 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 136 | 2023-02-15 | 2023-02-15 | 2023-02-01 | 14 | 2023-02-15 | 2023-02-01 | 8 | 2023-02-15 | Teste Analytics/Sprint 3 | 2023-02-01 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 7 | Em homologação | Business | 1.0 | 4206 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 128 | 2023-03-02 | 2023-03-02 | 2023-02-16 | 14 | 2023-03-02 | 2023-02-16 | 27 | 2023-03-02 | Dev. Analytics/Sprint 4 | 2023-02-16 | 14 | 3 - Baixa | Projeto 3 | Projeto1 |  | Backlog 8 | Concluído | Business | 1.0 | 4207 | Product Backlog Item
Teste Analytics | Ana Nogueira | 155 | 2023-03-26 | 2023-03-26 | 2023-02-16 | 38 | 2023-03-02 | 2023-02-16 | 28 | 2023-03-02 | Teste Analytics/Sprint 4 | 2023-02-16 | 38 | 1 - Alta | Projeto 1 | Projeto1 |  | Backlog 9 | Aberto | Business | 1.0 | 4208 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 128 | 2023-03-02 | 2023-03-02 | 2023-02-16 | 14 | 2023-03-02 | 2023-02-16 | 17 | 2023-03-02 | Análise de Requisitos/Sprint 4 | 2023-02-16 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Backlog 10 | Em atendimento | Business | 1.0 | 4209 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 101 | 2023-03-17 | 2023-03-17 | 2023-03-03 | 14 | 2023-03-17 | 2023-03-03 | 21 | 2023-03-17 | Dev. Analytics/Sprint 5 | 2023-03-03 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 11 | Em homologação | Business | 1.0 | 4210 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 46 | 2023-03-17 | 2023-03-17 | 2023-03-03 | 14 | 2023-03-17 | 2023-03-03 | 40 | 2023-03-17 | Dev. Analytics/Sprint 5 | 2023-03-03 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Backlog 12 | Aberto | Business | 1.0 | 4211 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 163 | 2023-04-01 | 2023-04-01 | 2023-03-18 | 14 | 2023-04-01 | 2023-03-18 | 23 | 2023-04-01 | Análise de Requisitos/Sprint 6 | 2023-03-18 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 13 | Em homologação | Business | 1.0 | 4212 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 31 | 2023-04-01 | 2023-04-01 | 2023-03-18 | 14 | 2023-04-01 | 2023-03-18 | 27 | 2023-04-01 | Análise de Requisitos/Sprint 6 | 2023-03-18 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 14 | Em atendimento | Business | 1.0 | 4213 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 128 | 2023-04-01 | 2023-04-01 | 2023-03-18 | 14 | 2023-04-01 | 2023-03-18 | 21 | 2023-04-01 | Teste Analytics/Sprint 6 | 2023-03-18 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 15 | Em atendimento | Business | 1.0 | 4214 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 34 | 2023-05-31 | 2023-05-31 | 2023-03-18 | 74 | 2023-04-01 | 2023-03-18 | 16 | 2023-04-01 | Análise de Requisitos/Sprint 6 | 2023-03-18 | 74 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 16 | Concluído | Business | 1.0 | 4215 | Product Backlog Item
Teste Analytics | Ana Nogueira | 161 | 2023-04-16 | 2023-04-16 | 2023-04-02 | 14 | 2023-04-16 | 2023-04-02 | 26 | 2023-04-16 | Teste Analytics/Sprint 7 | 2023-04-02 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Backlog 17 | Em homologação | Business | 1.0 | 4216 | Product Backlog Item
Dev. Analytics | Enzo Farias | 196 | 2023-04-16 | 2023-04-16 | 2023-04-02 | 14 | 2023-04-16 | 2023-04-02 | 26 | 2023-04-16 | Dev. Analytics/Sprint 7 | 2023-04-02 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Backlog 18 | Em atendimento | Business | 1.0 | 4217 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 53 | 2023-05-24 | 2023-05-24 | 2023-04-02 | 52 | 2023-04-16 | 2023-04-02 | 33 | 2023-04-16 | Teste Analytics/Sprint 7 | 2023-04-02 | 52 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Backlog 19 | Aberto | Business | 1.0 | 4218 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 149 | 2023-06-20 | 2023-06-20 | 2023-04-17 | 64 | 2023-05-01 | 2023-04-17 | 38 | 2023-05-01 | Dev. Analytics/Sprint 8 | 2023-04-17 | 64 | 3 - Baixa | Projeto 3 | Projeto1 |  | Backlog 20 | Em atendimento | Business | 1.0 | 4219 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 123 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 15 | 2023-05-16 | Dev. Analytics/Sprint 9 | 2023-05-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Backlog 21 | Concluído | Business | 1.0 | 4220 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 56 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 20 | 2023-05-16 | Análise de Requisitos/Sprint 9 | 2023-05-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Backlog 22 | Em atendimento | Business | 1.0 | 4221 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 146 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 18 | 2023-05-16 | Teste Analytics/Sprint 9 | 2023-05-02 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 23 | Aberto | Business | 1.0 | 4222 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 84 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 9 | 2023-05-16 | Teste Analytics/Sprint 9 | 2023-05-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Backlog 24 | Aberto | Business | 1.0 | 4223 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 89 | 2023-06-15 | 2023-06-15 | 2023-05-02 | 44 | 2023-05-16 | 2023-05-02 | 9 | 2023-05-16 | Dev. Analytics/Sprint 9 | 2023-05-02 | 44 | 2 - Média | Projeto 1 | Projeto2 |  | Backlog 25 | Em atendimento | Business | 1.0 | 4224 | Product Backlog Item
Teste Analytics | Enzo Farias | 100 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 18 | 2023-05-16 | Teste Analytics/Sprint 9 | 2023-05-02 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 26 | Em atendimento | Business | 1.0 | 4225 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 134 | 2023-05-31 | 2023-05-31 | 2023-05-17 | 14 | 2023-05-31 | 2023-05-17 | 27 | 2023-05-31 | Análise de Requisitos/Sprint 10 | 2023-05-17 | 14 | 2 - Média | Projeto 3 | Projeto3 |  | Backlog 27 | Em atendimento | Business | 1.0 | 4226 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 183 | 2023-05-31 | 2023-05-31 | 2023-05-17 | 14 | 2023-05-31 | 2023-05-17 | 32 | 2023-05-31 | Dev. Analytics/Sprint 10 | 2023-05-17 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 28 | Aberto | Business | 1.0 | 4227 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 21 | 2023-05-31 | 2023-05-31 | 2023-05-17 | 14 | 2023-05-31 | 2023-05-17 | 12 | 2023-05-31 | Análise de Requisitos/Sprint 10 | 2023-05-17 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Backlog 29 | Concluído | Business | 1.0 | 4228 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 197 | 2023-06-15 | 2023-06-15 | 2023-06-01 | 14 | 2023-06-15 | 2023-06-01 | 32 | 2023-06-15 | Análise de Requisitos/Sprint 11 | 2023-06-01 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 30 | Concluído | Business | 1.0 | 4229 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 124 | 2023-08-11 | 2023-08-11 | 2023-06-01 | 71 | 2023-06-15 | 2023-06-01 | 9 | 2023-06-15 | Análise de Requisitos/Sprint 11 | 2023-06-01 | 71 | 1 - Alta | Projeto 3 | Projeto2 |  | Backlog 31 | Concluído | Business | 1.0 | 4230 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 126 | 2023-06-15 | 2023-06-15 | 2023-06-01 | 14 | 2023-06-15 | 2023-06-01 | 23 | 2023-06-15 | Dev. Analytics/Sprint 11 | 2023-06-01 | 14 | 2 - Média | Projeto 1 | Projeto3 |  | Backlog 32 | Aberto | Business | 1.0 | 4231 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 156 | 2023-06-15 | 2023-06-15 | 2023-06-01 | 14 | 2023-06-15 | 2023-06-01 | 33 | 2023-06-15 | Dev. Analytics/Sprint 11 | 2023-06-01 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 33 | Em homologação | Business | 1.0 | 4232 | Product Backlog Item
Teste Analytics | Ana Nogueira | 63 | 2023-06-15 | 2023-06-15 | 2023-06-01 | 14 | 2023-06-15 | 2023-06-01 | 29 | 2023-06-15 | Teste Analytics/Sprint 11 | 2023-06-01 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Backlog 34 | Em atendimento | Business | 1.0 | 4233 | Product Backlog Item
Dev. Analytics | Enzo Farias | 140 | 2023-07-17 | 2023-07-17 | 2023-06-01 | 46 | 2023-06-15 | 2023-06-01 | 34 | 2023-06-15 | Dev. Analytics/Sprint 11 | 2023-06-01 | 46 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 35 | Em homologação | Business | 1.0 | 4234 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 42 | 2023-06-30 | 2023-06-30 | 2023-06-16 | 14 | 2023-06-30 | 2023-06-16 | 24 | 2023-06-30 | Análise de Requisitos/Sprint 12 | 2023-06-16 | 14 | 2 - Média | Projeto 1 | Projeto3 |  | Backlog 36 | Aberto | Business | 1.0 | 4235 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 29 | 2023-07-15 | 2023-07-15 | 2023-07-01 | 14 | 2023-07-15 | 2023-07-01 | 30 | 2023-07-15 | Dev. Analytics/Sprint 13 | 2023-07-01 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 37 | Aberto | Business | 1.0 | 4236 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 142 | 2023-07-15 | 2023-07-15 | 2023-07-01 | 14 | 2023-07-15 | 2023-07-01 | 22 | 2023-07-15 | Análise de Requisitos/Sprint 13 | 2023-07-01 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 38 | Concluído | Business | 1.0 | 4237 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 68 | 2023-09-20 | 2023-09-20 | 2023-07-16 | 66 | 2023-07-30 | 2023-07-16 | 37 | 2023-07-30 | Análise de Requisitos/Sprint 14 | 2023-07-16 | 66 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 39 | Concluído | Business | 1.0 | 4238 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 31 | 2023-07-30 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | 2023-07-16 | 24 | 2023-07-30 | Dev. Analytics/Sprint 14 | 2023-07-16 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Backlog 40 | Aberto | Business | 1.0 | 4239 | Product Backlog Item
Teste Analytics | Ana Nogueira | 27 | 2023-07-30 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | 2023-07-16 | 18 | 2023-07-30 | Teste Analytics/Sprint 14 | 2023-07-16 | 14 | 2 - Média | Projeto 3 | Projeto2 |  | Backlog 41 | Aberto | Business | 1.0 | 4240 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 38 | 2023-07-30 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | Teste Analytics/Sprint 14 | 2023-07-16 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 42 | Aberto | Business | 1.0 | 4241 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 21 | 2023-07-30 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | 2023-07-16 | 21 | 2023-07-30 | Dev. Analytics/Sprint 14 | 2023-07-16 | 14 | 2 - Média | Projeto 1 | Projeto2 |  | Backlog 43 | Concluído | Business | 1.0 | 4242 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 183 | 2023-08-14 | 2023-08-14 | 2023-07-31 | 14 | 2023-08-14 | 2023-07-31 | 27 | 2023-08-14 | Teste Analytics/Sprint 15 | 2023-07-31 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 44 | Em homologação | Business | 1.0 | 4243 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 187 | 2023-08-29 | 2023-08-29 | 2023-08-15 | 14 | 2023-08-29 | 2023-08-15 | 38 | 2023-08-29 | Dev. Analytics/Sprint 16 | 2023-08-15 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Backlog 45 | Em atendimento | Business | 1.0 | 4244 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 68 | 2023-08-29 | 2023-08-29 | 2023-08-15 | 14 | 2023-08-29 | 2023-08-15 | 25 | 2023-08-29 | Teste Analytics/Sprint 16 | 2023-08-15 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 46 | Aberto | Business | 1.0 | 4245 | Product Backlog Item
Teste Analytics | Ana Nogueira | 61 | 2023-09-13 | 2023-09-13 | 2023-08-30 | 14 | 2023-09-13 | 2023-08-30 | 33 | 2023-09-13 | Teste Analytics/Sprint 17 | 2023-08-30 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Backlog 47 | Concluído | Business | 1.0 | 4246 | Product Backlog Item
Teste Analytics | Ana Nogueira | 101 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 19 | 2023-09-28 | Teste Analytics/Sprint 18 | 2023-09-14 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 48 | Em atendimento | Business | 1.0 | 4247 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 181 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 18 | 2023-09-28 | Análise de Requisitos/Sprint 18 | 2023-09-14 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Backlog 49 | Em atendimento | Business | 1.0 | 4248 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 186 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 19 | 2023-09-28 | Análise de Requisitos/Sprint 18 | 2023-09-14 | 14 | 1 - Alta | Projeto 1 | Projeto1 |  | Backlog 50 | Concluído | Business | 1.0 | 4249 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 171 | 2023-11-22 | 2023-11-22 | 2023-09-14 | 69 | 2023-09-28 | 2023-09-14 | 20 | 2023-09-28 | Teste Analytics/Sprint 18 | 2023-09-14 | 69 | 2 - Média | Projeto 2 | Projeto2 |  | Backlog 51 | Concluído | Business | 1.0 | 4250 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 179 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 10 | 2023-09-28 | Dev. Analytics/Sprint 18 | 2023-09-14 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Backlog 52 | Concluído | Business | 1.0 | 4251 | Product Backlog Item
Teste Analytics | Ana Nogueira | 113 | 2023-11-09 | 2023-11-09 | 2023-09-29 | 41 | 2023-10-13 | 2023-09-29 | 30 | 2023-10-13 | Teste Analytics/Sprint 19 | 2023-09-29 | 41 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 53 | Em homologação | Business | 1.0 | 4252 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 148 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 11 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 54 | Em homologação | Business | 1.0 | 4253 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 183 | 2023-12-20 | 2023-12-20 | 2023-10-14 | 67 | 2023-10-28 | 2023-10-14 | 34 | 2023-10-28 | Dev. Analytics/Sprint 20 | 2023-10-14 | 67 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 55 | Aberto | Business | 1.0 | 4254 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 169 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 34 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Backlog 56 | Em atendimento | Business | 1.0 | 4255 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 31 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 22 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Backlog 57 | Em homologação | Business | 1.0 | 4256 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 95 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 25 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto1 |  | Backlog 58 | Concluído | Business | 1.0 | 4257 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 56 | 2023-11-28 | 2023-11-28 | 2023-10-29 | 30 | 2023-11-12 | 2023-10-29 | 23 | 2023-11-12 | Análise de Requisitos/Sprint 21 | 2023-10-29 | 30 | 3 - Baixa | Projeto 2 | Projeto1 |  | Backlog 59 | Concluído | Business | 1.0 | 4258 | Product Backlog Item
Teste Analytics | Enzo Farias | 191 | 2023-12-20 | 2023-12-20 | 2023-10-29 | 52 | 2023-11-12 | 2023-10-29 | 31 | 2023-11-12 | Teste Analytics/Sprint 21 | 2023-10-29 | 52 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 60 | Em homologação | Business | 1.0 | 4259 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 23 | 2023-12-06 | 2023-12-06 | 2023-10-29 | 38 | 2023-11-12 | 2023-10-29 | 31 | 2023-11-12 | Análise de Requisitos/Sprint 21 | 2023-10-29 | 38 | 1 - Alta | Projeto 2 | Projeto2 |  | Backlog 61 | Em homologação | Business | 1.0 | 4260 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 124 | 2023-11-12 | 2023-11-12 | 2023-10-29 | 14 | 2023-11-12 | 2023-10-29 | 23 | 2023-11-12 | Dev. Analytics/Sprint 21 | 2023-10-29 | 14 | 2 - Média | Projeto 2 | Projeto2 |  | Backlog 62 | Aberto | Business | 1.0 | 4261 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 137 | 2023-11-12 | 2023-11-12 | 2023-10-29 | 14 | 2023-11-12 | 2023-10-29 | 14 | 2023-11-12 | Análise de Requisitos/Sprint 21 | 2023-10-29 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Backlog 63 | Concluído | Business | 1.0 | 4262 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 172 | 2023-12-06 | 2023-12-06 | 2023-10-29 | 38 | 2023-11-12 | 2023-10-29 | 39 | 2023-11-12 | Dev. Analytics/Sprint 21 | 2023-10-29 | 38 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 64 | Em atendimento | Business | 1.0 | 4263 | Product Backlog Item
Teste Analytics | Ana Nogueira | 149 | 2023-11-12 | 2023-11-12 | 2023-10-29 | 14 | 2023-11-12 | 2023-10-29 | 24 | 2023-11-12 | Teste Analytics/Sprint 21 | 2023-10-29 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 65 | Em atendimento | Business | 1.0 | 4264 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 143 | 2024-01-13 | 2024-01-13 | 2023-11-13 | 61 | 2023-11-27 | 2023-11-13 | 16 | 2023-11-27 | Análise de Requisitos/Sprint 22 | 2023-11-13 | 61 | 2 - Média | Projeto 3 | Projeto1 |  | Backlog 66 | Aberto | Business | 1.0 | 4265 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 159 | 2023-12-12 | 2023-12-12 | 2023-11-28 | 14 | 2023-12-12 | 2023-11-28 | 10 | 2023-12-12 | Dev. Analytics/Sprint 23 | 2023-11-28 | 14 | 2 - Média | Projeto 3 | Projeto3 |  | Backlog 67 | Em atendimento | Business | 1.0 | 4266 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 129 | 2024-01-17 | 2024-01-17 | 2023-11-28 | 50 | 2023-12-12 | 2023-11-28 | 10 | 2023-12-12 | Dev. Analytics/Sprint 23 | 2023-11-28 | 50 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 68 | Concluído | Business | 1.0 | 4267 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 86 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 15 | 2023-12-27 | Análise de Requisitos/Sprint 24 | 2023-12-13 | 14 | 2 - Média | Projeto 2 | Projeto1 |  | Backlog 69 | Em homologação | Business | 1.0 | 4268 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 145 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 28 | 2023-12-27 | Análise de Requisitos/Sprint 24 | 2023-12-13 | 14 | 3 - Baixa | Projeto 2 | Projeto2 |  | Backlog 70 | Em atendimento | Business | 1.0 | 4269 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 174 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 27 | 2023-12-27 | Dev. Analytics/Sprint 24 | 2023-12-13 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Backlog 71 | Concluído | Business | 1.0 | 4270 | Product Backlog Item
Teste Analytics | Ana Nogueira | 151 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 31 | 2023-12-27 | Teste Analytics/Sprint 24 | 2023-12-13 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 72 | Em homologação | Business | 1.0 | 4271 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 120 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 35 | 2023-12-27 | Dev. Analytics/Sprint 24 | 2023-12-13 | 14 | 1 - Alta | Projeto 3 | Projeto1 |  | Backlog 73 | Aberto | Business | 1.0 | 4272 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 81 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 15 | 2023-12-27 | Teste Analytics/Sprint 24 | 2023-12-13 | 14 | 2 - Média | Projeto 1 | Projeto2 |  | Backlog 74 | Aberto | Business | 1.0 | 4273 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 59 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 20 | 2023-12-27 | Análise de Requisitos/Sprint 24 | 2023-12-13 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Backlog 75 | Em atendimento | Business | 1.0 | 4274 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 48 | 2024-01-29 | 2024-01-29 | 2023-12-28 | 32 | 2024-01-11 | 2023-12-28 | 17 | 2024-01-11 | Dev. Analytics/Sprint 25 | 2023-12-28 | 32 | 3 - Baixa | Projeto 3 | Projeto3 |  | Backlog 76 | Aberto | Business | 1.0 | 4275 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 175 | 2024-01-30 | 2024-01-30 | 2023-12-28 | 33 | 2024-01-11 | 2023-12-28 | 12 | 2024-01-11 | Dev. Analytics/Sprint 25 | 2023-12-28 | 33 | 2 - Média | Projeto 3 | Projeto2 |  | Backlog 77 | Aberto | Business | 1.0 | 4276 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 185 | 2024-02-25 | 2024-02-25 | 2023-12-28 | 59 | 2024-01-11 | 2023-12-28 | 34 | 2024-01-11 | Teste Analytics/Sprint 25 | 2023-12-28 | 59 | 3 - Baixa | Projeto 2 | Projeto2 |  | Backlog 78 | Concluído | Business | 1.0 | 4277 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 105 | 2024-03-12 | 2024-03-12 | 2024-01-12 | 60 | 2024-01-26 | 2024-01-12 | 35 | 2024-01-26 | Análise de Requisitos/Sprint 26 | 2024-01-12 | 60 | 1 - Alta | Projeto 2 | Projeto3 |  | Backlog 79 | Concluído | Business | 1.0 | 4278 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 172 | 2024-01-26 | 2024-01-26 | 2024-01-12 | 14 | 2024-01-26 | 2024-01-12 | 15 | 2024-01-26 | Teste Analytics/Sprint 26 | 2024-01-12 | 14 | 2 - Média | Projeto 2 | Projeto1 |  | Backlog 80 | Concluído | Business | 1.0 | 4279 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 180 | 2024-03-07 | 2024-03-07 | 2024-01-12 | 55 | 2024-01-26 | 2024-01-12 | 32 | 2024-01-26 | Análise de Requisitos/Sprint 26 | 2024-01-12 | 55 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 81 | Em atendimento | Business | 1.0 | 4280 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 107 | 2024-02-10 | 2024-02-10 | 2024-01-27 | 14 | 2024-02-10 | 2024-01-27 | 31 | 2024-02-10 | Dev. Analytics/Sprint 27 | 2024-01-27 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Backlog 82 | Concluído | Business | 1.0 | 4281 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 26 | 2024-02-10 | 2024-02-10 | 2024-01-27 | 14 | 2024-02-10 | 2024-01-27 | 40 | 2024-02-10 | Análise de Requisitos/Sprint 27 | 2024-01-27 | 14 | 1 - Alta | Projeto 3 | Projeto2 |  | Backlog 83 | Em homologação | Business | 1.0 | 4282 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 186 | 2024-02-10 | 2024-02-10 | 2024-01-27 | 14 | 2024-02-10 | 2024-01-27 | 28 | 2024-02-10 | Dev. Analytics/Sprint 27 | 2024-01-27 | 14 | 3 - Baixa | Projeto 1 | Projeto3 |  | Backlog 84 | Em atendimento | Business | 1.0 | 4283 | Product Backlog Item
Teste Analytics | Enzo Farias | 49 | 2024-02-10 | 2024-02-10 | 2024-01-27 | 14 | 2024-02-10 | 2024-01-27 | 25 | 2024-02-10 | Teste Analytics/Sprint 27 | 2024-01-27 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Backlog 85 | Em homologação | Business | 1.0 | 4284 | Product Backlog Item
Teste Analytics | Ana Nogueira | 90 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 27 | 2024-02-25 | Teste Analytics/Sprint 28 | 2024-02-11 | 14 | 1 - Alta | Projeto 3 | Projeto1 |  | Backlog 86 | Em homologação | Business | 1.0 | 4285 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 82 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 31 | 2024-02-25 | Análise de Requisitos/Sprint 28 | 2024-02-11 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 87 | Em atendimento | Business | 1.0 | 4286 | Product Backlog Item
Dev. Analytics | Enzo Farias | 40 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | Dev. Analytics/Sprint 28 | 2024-02-11 | 14 | 3 - Baixa | Projeto 3 | Projeto3 |  | Backlog 88 | Em atendimento | Business | 1.0 | 4287 | Product Backlog Item
Teste Analytics | Ana Nogueira | 54 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 31 | 2024-02-25 | Teste Analytics/Sprint 28 | 2024-02-11 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Backlog 89 | Concluído | Business | 1.0 | 4288 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 120 | 2024-03-12 | 2024-03-12 | 2024-02-11 | 30 | 2024-02-25 | 2024-02-11 | 25 | 2024-02-25 | Teste Analytics/Sprint 28 | 2024-02-11 | 30 | 1 - Alta | Projeto 2 | Projeto2 |  | Backlog 90 | Em atendimento | Business | 1.0 | 4289 | Product Backlog Item
Teste Analytics | Enzo Farias | 57 | 2024-04-23 | 2024-04-23 | 2024-02-26 | 57 | 2024-03-11 | 2024-02-26 | 33 | 2024-03-11 | Teste Analytics/Sprint 29 | 2024-02-26 | 57 | 2 - Média | Projeto 1 | Projeto1 |  | Backlog 91 | Em atendimento | Business | 1.0 | 4290 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 143 | 2024-03-11 | 2024-03-11 | 2024-02-26 | 14 | 2024-03-11 | 2024-02-26 | 15 | 2024-03-11 | Análise de Requisitos/Sprint 29 | 2024-02-26 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 92 | Concluído | Business | 1.0 | 4291 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 21 | 2024-03-11 | 2024-03-11 | 2024-02-26 | 14 | 2024-03-11 | 2024-02-26 | 20 | 2024-03-11 | Teste Analytics/Sprint 29 | 2024-02-26 | 14 | 2 - Média | Projeto 2 | Projeto1 |  | Backlog 93 | Aberto | Business | 1.0 | 4292 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 126 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 24 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 94 | Em homologação | Business | 1.0 | 4293 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 87 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 22 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 2 - Média | Projeto 1 | Projeto3 |  | Backlog 95 | Concluído | Business | 1.0 | 4294 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 108 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 23 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 96 | Concluído | Business | 1.0 | 4295 | Product Backlog Item
Teste Analytics | Ana Nogueira | 200 | 2024-04-17 | 2024-04-17 | 2024-03-12 | 36 | 2024-03-26 | 2024-03-12 | 23 | 2024-03-26 | Teste Analytics/Sprint 30 | 2024-03-12 | 36 | 3 - Baixa | Projeto 3 | Projeto3 |  | Backlog 97 | Aberto | Business | 1.0 | 4296 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 73 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 21 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 1 - Alta | Projeto 1 | Projeto2 |  | Backlog 98 | Em atendimento | Business | 1.0 | 4297 | Product Backlog Item
Dev. Analytics | Enzo Farias | 196 | 2024-04-28 | 2024-04-28 | 2024-03-12 | 47 | 2024-03-26 | 2024-03-12 | 25 | 2024-03-26 | Dev. Analytics/Sprint 30 | 2024-03-12 | 47 | 1 - Alta | Projeto 3 | Projeto2 |  | Backlog 99 | Aberto | Business | 1.0 | 4298 | Product Backlog Item
Dev. Analytics | Enzo Farias | 97 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 19 | 2024-03-26 | Dev. Analytics/Sprint 30 | 2024-03-12 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto1 |  | Backlog 100 | Concluído | Business | 1.0 | 4299 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 67 | 2024-05-14 | 2024-05-14 | 2024-03-27 | 48 | 2024-04-10 | 2024-03-27 | 36 | 2024-04-10 | Análise de Requisitos/Sprint 31 | 2024-03-27 | 48 | 3 - Baixa | Projeto 2 | Projeto2 |  | Backlog 101 | Em homologação | Business | 1.0 | 4300 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 112 | 2024-04-10 | 2024-04-10 | 2024-03-27 | 14 | 2024-04-10 | 2024-03-27 | 30 | 2024-04-10 | Análise de Requisitos/Sprint 31 | 2024-03-27 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 102 | Em homologação | Business | 1.0 | 4301 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 147 | 2024-04-10 | 2024-04-10 | 2024-03-27 | 14 | 2024-04-10 | 2024-03-27 | 23 | 2024-04-10 | Análise de Requisitos/Sprint 31 | 2024-03-27 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Backlog 103 | Aberto | Business | 1.0 | 4302 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 39 | 2024-04-10 | 2024-04-10 | 2024-03-27 | 14 | 2024-04-10 | 2024-03-27 | 30 | 2024-04-10 | Dev. Analytics/Sprint 31 | 2024-03-27 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Backlog 104 | Em homologação | Business | 1.0 | 4303 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 135 | 2024-06-05 | 2024-06-05 | 2024-04-11 | 55 | 2024-04-25 | 2024-04-11 | 18 | 2024-04-25 | Dev. Analytics/Sprint 32 | 2024-04-11 | 55 | 1 - Alta | Projeto 1 | Projeto2 |  | Backlog 105 | Em homologação | Business | 1.0 | 4304 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 145 | 2024-04-25 | 2024-04-25 | 2024-04-11 | 14 | 2024-04-25 | 2024-04-11 | 23 | 2024-04-25 | Teste Analytics/Sprint 32 | 2024-04-11 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 106 | Em homologação | Business | 1.0 | 4305 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 164 | 2024-06-24 | 2024-06-24 | 2024-04-11 | 74 | 2024-04-25 | 2024-04-11 | 12 | 2024-04-25 | Dev. Analytics/Sprint 32 | 2024-04-11 | 74 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 107 | Em homologação | Business | 1.0 | 4306 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 171 | 2024-05-25 | 2024-05-25 | 2024-04-11 | 44 | 2024-04-25 | 2024-04-11 | 20 | 2024-04-25 | Teste Analytics/Sprint 32 | 2024-04-11 | 44 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Backlog 108 | Em homologação | Business | 1.0 | 4307 | Product Backlog Item
Teste Analytics | Ana Nogueira | 46 | 2024-04-25 | 2024-04-25 | 2024-04-11 | 14 | 2024-04-25 | 2024-04-11 | 21 | 2024-04-25 | Teste Analytics/Sprint 32 | 2024-04-11 | 14 | 1 - Alta | Projeto 3 | Projeto2 |  | Backlog 109 | Concluído | Business | 1.0 | 4308 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 157 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 9 | 2024-05-10 | Dev. Analytics/Sprint 33 | 2024-04-26 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Backlog 110 | Concluído | Business | 1.0 | 4309 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 127 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 28 | 2024-05-10 | Dev. Analytics/Sprint 33 | 2024-04-26 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Backlog 111 | Aberto | Business | 1.0 | 4310 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 140 | 2024-07-03 | 2024-07-03 | 2024-04-26 | 68 | 2024-05-10 | 2024-04-26 | 23 | 2024-05-10 | Dev. Analytics/Sprint 33 | 2024-04-26 | 68 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 112 | Concluído | Business | 1.0 | 4311 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 140 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 17 | 2024-05-10 | Análise de Requisitos/Sprint 33 | 2024-04-26 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Backlog 113 | Concluído | Business | 1.0 | 4312 | Product Backlog Item
Teste Analytics | Enzo Farias | 40 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 9 | 2024-05-10 | Teste Analytics/Sprint 33 | 2024-04-26 | 14 | 1 - Alta | Projeto 3 | Projeto2 |  | Backlog 114 | Em atendimento | Business | 1.0 | 4313 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 38 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 18 | 2024-05-10 | Dev. Analytics/Sprint 33 | 2024-04-26 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Backlog 115 | Aberto | Business | 1.0 | 4314 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 53 | 2024-05-25 | 2024-05-25 | 2024-05-11 | 14 | 2024-05-25 | 2024-05-11 | 10 | 2024-05-25 | Teste Analytics/Sprint 34 | 2024-05-11 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Backlog 116 | Concluído | Business | 1.0 | 4315 | Product Backlog Item
Teste Analytics | Enzo Farias | 86 | 2024-07-22 | 2024-07-22 | 2024-05-11 | 72 | 2024-05-25 | 2024-05-11 | 23 | 2024-05-25 | Teste Analytics/Sprint 34 | 2024-05-11 | 72 | 2 - Média | Projeto 2 | Projeto2 |  | Backlog 117 | Em atendimento | Business | 1.0 | 4316 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 30 | 2024-05-25 | 2024-05-25 | 2024-05-11 | 14 | 2024-05-25 | 2024-05-11 | 17 | 2024-05-25 | Dev. Analytics/Sprint 34 | 2024-05-11 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Backlog 118 | Em atendimento | Business | 1.0 | 4317 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 112 | 2024-06-09 | 2024-06-09 | 2024-05-26 | 14 | 2024-06-09 | 2024-05-26 | 32 | 2024-06-09 | Dev. Analytics/Sprint 35 | 2024-05-26 | 14 | 1 - Alta | Projeto 2 | Projeto3 |  | Backlog 119 | Aberto | Business | 1.0 | 4318 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 87 | 2024-06-09 | 2024-06-09 | 2024-05-26 | 14 | 2024-06-09 | 2024-05-26 | 29 | 2024-06-09 | Dev. Analytics/Sprint 35 | 2024-05-26 | 14 | 2 - Média | Projeto 3 | Projeto2 |  | Backlog 120 | Concluído | Business | 1.0 | 4319 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 106 | 2024-06-09 | 2024-06-09 | 2024-05-26 | 14 | 2024-06-09 | 2024-05-26 | 16 | 2024-06-09 | Teste Analytics/Sprint 35 | 2024-05-26 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 121 | Concluído | Business | 1.0 | 4320 | Product Backlog Item
Teste Analytics | Ana Nogueira | 21 | 2024-07-02 | 2024-07-02 | 2024-05-26 | 37 | 2024-06-09 | 2024-05-26 | 15 | 2024-06-09 | Teste Analytics/Sprint 35 | 2024-05-26 | 37 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 122 | Em homologação | Business | 1.0 | 4321 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 151 | 2024-06-24 | 2024-06-24 | 2024-06-10 | 14 | 2024-06-24 | 2024-06-10 | 26 | 2024-06-24 | Teste Analytics/Sprint 36 | 2024-06-10 | 14 | 3 - Baixa | Projeto 1 | Projeto1 |  | Backlog 123 | Aberto | Business | 1.0 | 4322 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 166 | 2024-06-24 | 2024-06-24 | 2024-06-10 | 14 | 2024-06-24 | 2024-06-10 | 31 | 2024-06-24 | Teste Analytics/Sprint 36 | 2024-06-10 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Backlog 124 | Em atendimento | Business | 1.0 | 4323 | Product Backlog Item
Dev. Analytics | Enzo Farias | 54 | 2024-06-24 | 2024-06-24 | 2024-06-10 | 14 | 2024-06-24 | 2024-06-10 | 19 | 2024-06-24 | Dev. Analytics/Sprint 36 | 2024-06-10 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 125 | Em homologação | Business | 1.0 | 4324 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 136 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 16 | 2024-07-09 | Teste Analytics/Sprint 37 | 2024-06-25 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 126 | Aberto | Business | 1.0 | 4325 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 178 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 37 | 2024-07-09 | Análise de Requisitos/Sprint 37 | 2024-06-25 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 127 | Em homologação | Business | 1.0 | 4326 | Product Backlog Item
Teste Analytics | Ana Nogueira | 109 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 29 | 2024-07-09 | Teste Analytics/Sprint 37 | 2024-06-25 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Backlog 128 | Concluído | Business | 1.0 | 4327 | Product Backlog Item
Dev. Analytics | Enzo Farias | 99 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 13 | 2024-07-09 | Dev. Analytics/Sprint 37 | 2024-06-25 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Backlog 129 | Concluído | Business | 1.0 | 4328 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 146 | 2024-07-24 | 2024-07-24 | 2024-07-10 | 14 | 2024-07-24 | 2024-07-10 | 32 | 2024-07-24 | Análise de Requisitos/Sprint 38 | 2024-07-10 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 130 | Aberto | Business | 1.0 | 4329 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 55 | 2024-09-27 | 2024-09-27 | 2024-07-25 | 64 | 2024-08-08 | 2024-07-25 | 38 | 2024-08-08 | Teste Analytics/Sprint 39 | 2024-07-25 | 64 | 2 - Média | Projeto 1 | Projeto2 |  | Backlog 131 | Em atendimento | Business | 1.0 | 4330 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 39 | 2024-08-08 | 2024-08-08 | 2024-07-25 | 14 | 2024-08-08 | 2024-07-25 | 13 | 2024-08-08 | Análise de Requisitos/Sprint 39 | 2024-07-25 | 14 | 3 - Baixa | Projeto 1 | Projeto1 |  | Backlog 132 | Concluído | Business | 1.0 | 4331 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 150 | 2024-08-08 | 2024-08-08 | 2024-07-25 | 14 | 2024-08-08 | 2024-07-25 | 32 | 2024-08-08 | Teste Analytics/Sprint 39 | 2024-07-25 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Backlog 133 | Aberto | Business | 1.0 | 4332 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 169 | 2024-08-23 | 2024-08-23 | 2024-08-09 | 14 | 2024-08-23 | 2024-08-09 | 26 | 2024-08-23 | Teste Analytics/Sprint 40 | 2024-08-09 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 134 | Em atendimento | Business | 1.0 | 4333 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 180 | 2024-09-07 | 2024-09-07 | 2024-08-24 | 14 | 2024-09-07 | 2024-08-24 | 10 | 2024-09-07 | Teste Analytics/Sprint 41 | 2024-08-24 | 14 | 3 - Baixa | Projeto 2 | Projeto2 |  | Backlog 135 | Aberto | Business | 1.0 | 4334 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 116 | 2024-11-21 | 2024-11-21 | 2024-09-08 | 74 | 2024-09-22 | 2024-09-08 | 37 | 2024-09-22 | Teste Analytics/Sprint 42 | 2024-09-08 | 74 | 1 - Alta | Projeto 2 | Projeto2 |  | Backlog 136 | Concluído | Business | 1.0 | 4335 | Product Backlog Item
Teste Analytics | Ana Nogueira | 196 | 2024-09-22 | 2024-09-22 | 2024-09-08 | 14 | 2024-09-22 | 2024-09-08 | 21 | 2024-09-22 | Teste Analytics/Sprint 42 | 2024-09-08 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Backlog 137 | Em homologação | Business | 1.0 | 4336 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 63 | 2024-09-22 | 2024-09-22 | 2024-09-08 | 14 | 2024-09-22 | 2024-09-08 | 10 | 2024-09-22 | Análise de Requisitos/Sprint 42 | 2024-09-08 | 14 | 2 - Média | Projeto 2 | Projeto2 |  | Backlog 138 | Em homologação | Business | 1.0 | 4337 | Product Backlog Item
Dev. Analytics | Enzo Farias | 137 | 2024-10-07 | 2024-10-07 | 2024-09-23 | 14 | 2024-10-07 | 2024-09-23 | 23 | 2024-10-07 | Dev. Analytics/Sprint 43 | 2024-09-23 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Backlog 139 | Concluído | Business | 1.0 | 4338 | Product Backlog Item
Teste Analytics | Ana Nogueira | 131 | 2024-10-22 | 2024-10-22 | 2024-10-08 | 14 | 2024-10-22 | 2024-10-08 | 20 | 2024-10-22 | Teste Analytics/Sprint 44 | 2024-10-08 | 14 | 1 - Alta | Projeto 2 | Projeto3 |  | Backlog 140 | Em atendimento | Business | 1.0 | 4339 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 123 | 2024-12-12 | 2024-12-12 | 2024-10-08 | 65 | 2024-10-22 | 2024-10-08 | 23 | 2024-10-22 | Análise de Requisitos/Sprint 44 | 2024-10-08 | 65 | 2 - Média | Projeto 1 | Projeto2 |  | Backlog 141 | Aberto | Business | 1.0 | 4340 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 161 | 2024-11-06 | 2024-11-06 | 2024-10-23 | 14 | 2024-11-06 | 2024-10-23 | 31 | 2024-11-06 | Teste Analytics/Sprint 45 | 2024-10-23 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 142 | Aberto | Business | 1.0 | 4341 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 161 | 2024-11-06 | 2024-11-06 | 2024-10-23 | 14 | 2024-11-06 | 2024-10-23 | 8 | 2024-11-06 | Análise de Requisitos/Sprint 45 | 2024-10-23 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Backlog 143 | Em atendimento | Business | 1.0 | 4342 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 126 | 2024-11-06 | 2024-11-06 | 2024-10-23 | 14 | 2024-11-06 | 2024-10-23 | 14 | 2024-11-06 | Dev. Analytics/Sprint 45 | 2024-10-23 | 14 | 1 - Alta | Projeto 2 | Projeto3 |  | Backlog 144 | Em atendimento | Business | 1.0 | 4343 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 156 | 2024-12-23 | 2024-12-23 | 2024-11-07 | 46 | 2024-11-21 | 2024-11-07 | 27 | 2024-11-21 | Dev. Analytics/Sprint 46 | 2024-11-07 | 46 | 2 - Média | Projeto 1 | Projeto3 |  | Backlog 145 | Em atendimento | Business | 1.0 | 4344 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 130 | 2025-01-11 | 2025-01-11 | 2024-11-07 | 65 | 2024-11-21 | 2024-11-07 | 29 | 2024-11-21 | Teste Analytics/Sprint 46 | 2024-11-07 | 65 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 146 | Concluído | Business | 1.0 | 4345 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 95 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 12 | 2024-12-06 | Análise de Requisitos/Sprint 47 | 2024-11-22 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Backlog 147 | Em homologação | Business | 1.0 | 4346 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 37 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 28 | 2024-12-06 | Análise de Requisitos/Sprint 47 | 2024-11-22 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 148 | Aberto | Business | 1.0 | 4347 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 200 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 18 | 2024-12-06 | Análise de Requisitos/Sprint 47 | 2024-11-22 | 14 | 1 - Alta | Projeto 3 | Projeto1 |  | Backlog 149 | Em atendimento | Business | 1.0 | 4348 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 196 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 18 | 2024-12-06 | Análise de Requisitos/Sprint 47 | 2024-11-22 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Backlog 150 | Concluído | Business | 1.0 | 4349 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 139 | 2024-12-21 | 2024-12-21 | 2024-12-07 | 14 | 2024-12-21 | 2024-12-07 | 39 | 2024-12-21 | Análise de Requisitos/Sprint 48 | 2024-12-07 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Backlog 151 | Concluído | Business | 1.0 | 4350 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 58 | 2025-01-05 | 2025-01-05 | 2024-12-22 | 14 | 2025-01-05 | 2024-12-22 | 26 | 2025-01-05 | Teste Analytics/Sprint 49 | 2024-12-22 | 14 | 1 - Alta | Projeto 3 | Projeto1 |  | Backlog 152 | Em homologação | Business | 1.0 | 4351 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 189 | 2025-01-05 | 2025-01-05 | 2024-12-22 | 14 | 2025-01-05 | 2024-12-22 | 19 | 2025-01-05 | Análise de Requisitos/Sprint 49 | 2024-12-22 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Backlog 153 | Em homologação | Business | 1.0 | 4352 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 121 | 2025-01-05 | 2025-01-05 | 2024-12-22 | 14 | 2025-01-05 | 2024-12-22 | 25 | 2025-01-05 | Análise de Requisitos/Sprint 49 | 2024-12-22 | 14 | 3 - Baixa | Projeto 3 | Projeto3 |  | Backlog 154 | Concluído | Business | 1.0 | 4353 | Product Backlog Item