## Sheet1
Area Path | Assigned To | Business Value | Changed Date | Closed Date | Created Date | Cycle Time Days | Data Fim Previsto | Data Início Previsto | Effort | Iteration End Date | Iteration Path | Iteration Start Date | Lead Time Days | Priority | Project Name | Service Now | Tags | Title | Value Area | Versão | Work Item Id | Work Item Type
Dev. Analytics | Bárbara Andrade | 75 | 2023-03-01 | 2023-03-01 | 2023-01-02 | 58 | 2023-01-16 | 2023-01-02 | 36 | 2023-01-16 | Dev. Analytics/Sprint 1 | 2023-01-02 | 58 | 1 - Alta | Projeto 1 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4200 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 35 | 2023-01-31 | 2023-01-31 | 2023-01-17 | 14 | 2023-01-31 | 2023-01-17 | 27 | 2023-01-31 | Dev. Analytics/Sprint 2 | 2023-01-17 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4201 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 142 | 2023-01-31 | 2023-01-31 | 2023-01-17 | 14 | 2023-01-31 | 2023-01-17 | 38 | 2023-01-31 | Dev. Analytics/Sprint 2 | 2023-01-17 | 14 | 3 - Baixa | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4202 | Product Backlog Item
Teste Analytics | Ana Nogueira | 196 | 2023-01-31 | 2023-01-31 | 2023-01-17 | 14 | 2023-01-31 | 2023-01-17 | 28 | 2023-01-31 | Teste Analytics/Sprint 2 | 2023-01-17 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4203 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 96 | 2023-02-15 | 2023-02-15 | 2023-02-01 | 14 | 2023-02-15 | 2023-02-01 | 16 | 2023-02-15 | Teste Analytics/Sprint 3 | 2023-02-01 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4204 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 32 | 2023-02-15 | 2023-02-15 | 2023-02-01 | 14 | 2023-02-15 | 2023-02-01 | 25 | 2023-02-15 | Dev. Analytics/Sprint 3 | 2023-02-01 | 14 | 3 - Baixa | Projeto 1 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4205 | Product Backlog Item
Teste Analytics | Enzo Farias | 74 | 2023-03-18 | 2023-03-18 | 2023-02-16 | 30 | 2023-03-02 | 2023-02-16 | 12 | 2023-03-02 | Teste Analytics/Sprint 4 | 2023-02-16 | 30 | 2 - Média | Projeto 2 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4206 | Product Backlog Item
Teste Analytics | Enzo Farias | 96 | 2023-03-02 | 2023-03-02 | 2023-02-16 | 14 | 2023-03-02 | 2023-02-16 | 32 | 2023-03-02 | Teste Analytics/Sprint 4 | 2023-02-16 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4207 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 154 | 2023-03-02 | 2023-03-02 | 2023-02-16 | 14 | 2023-03-02 | 2023-02-16 | 31 | 2023-03-02 | Teste Analytics/Sprint 4 | 2023-02-16 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4208 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 200 | 2023-04-15 | 2023-04-15 | 2023-03-03 | 43 | 2023-03-17 | 2023-03-03 | 40 | 2023-03-17 | Dev. Analytics/Sprint 5 | 2023-03-03 | 43 | 3 - Baixa | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4209 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 138 | 2023-03-17 | 2023-03-17 | 2023-03-03 | 14 | 2023-03-17 | 2023-03-03 | 15 | 2023-03-17 | Dev. Analytics/Sprint 5 | 2023-03-03 | 14 | 2 - Média | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4210 | Product Backlog Item
Teste Analytics | Ana Nogueira | 130 | 2023-04-01 | 2023-04-01 | 2023-03-18 | 14 | 2023-04-01 | 2023-03-18 | 40 | 2023-04-01 | Teste Analytics/Sprint 6 | 2023-03-18 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4211 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 106 | 2023-04-16 | 2023-04-16 | 2023-04-02 | 14 | 2023-04-16 | 2023-04-02 | 9 | 2023-04-16 | Dev. Analytics/Sprint 7 | 2023-04-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4212 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 181 | 2023-05-01 | 2023-05-01 | 2023-04-17 | 14 | 2023-05-01 | 2023-04-17 | 38 | 2023-05-01 | Análise de Requisitos/Sprint 8 | 2023-04-17 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4213 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 59 | 2023-05-01 | 2023-05-01 | 2023-04-17 | 14 | 2023-05-01 | 2023-04-17 | 36 | 2023-05-01 | Dev. Analytics/Sprint 8 | 2023-04-17 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4214 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 170 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 38 | 2023-05-16 | Teste Analytics/Sprint 9 | 2023-05-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4215 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 114 | 2023-05-16 | 2023-05-16 | 2023-05-02 | 14 | 2023-05-16 | 2023-05-02 | 34 | 2023-05-16 | Análise de Requisitos/Sprint 9 | 2023-05-02 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4216 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 71 | 2023-05-31 | 2023-05-31 | 2023-05-17 | 14 | 2023-05-31 | 2023-05-17 | 20 | 2023-05-31 | Análise de Requisitos/Sprint 10 | 2023-05-17 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4217 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 32 | 2023-06-18 | 2023-06-18 | 2023-05-17 | 32 | 2023-05-31 | 2023-05-17 | 40 | 2023-05-31 | Dev. Analytics/Sprint 10 | 2023-05-17 | 32 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4218 | Product Backlog Item
Teste Analytics | Ana Nogueira | 146 | 2023-07-30 | 2023-07-30 | 2023-05-17 | 74 | 2023-05-31 | 2023-05-17 | 36 | 2023-05-31 | Teste Analytics/Sprint 10 | 2023-05-17 | 74 | 3 - Baixa | Projeto 1 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4219 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 178 | 2023-06-15 | 2023-06-15 | 2023-06-01 | 14 | 2023-06-15 | 2023-06-01 | 21 | 2023-06-15 | Análise de Requisitos/Sprint 11 | 2023-06-01 | 14 | 2 - Média | Projeto 3 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4220 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 136 | 2023-07-01 | 2023-07-01 | 2023-06-01 | 30 | 2023-06-15 | 2023-06-01 | 35 | 2023-06-15 | Dev. Analytics/Sprint 11 | 2023-06-01 | 30 | 2 - Média | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4221 | Product Backlog Item
Teste Analytics | Ana Nogueira | 179 | 2023-08-13 | 2023-08-13 | 2023-06-01 | 73 | 2023-06-15 | 2023-06-01 | 36 | 2023-06-15 | Teste Analytics/Sprint 11 | 2023-06-01 | 73 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4222 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 73 | 2023-06-30 | 2023-06-30 | 2023-06-16 | 14 | 2023-06-30 | 2023-06-16 | 20 | 2023-06-30 | Dev. Analytics/Sprint 12 | 2023-06-16 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4223 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 179 | 2023-07-15 | 2023-07-15 | 2023-07-01 | 14 | 2023-07-15 | 2023-07-01 | 30 | 2023-07-15 | Teste Analytics/Sprint 13 | 2023-07-01 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4224 | Product Backlog Item
Dev. Analytics | Enzo Farias | 105 | 2023-09-13 | 2023-09-13 | 2023-07-01 | 74 | 2023-07-15 | 2023-07-01 | 29 | 2023-07-15 | Dev. Analytics/Sprint 13 | 2023-07-01 | 74 | 1 - Alta | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4225 | Product Backlog Item
Teste Analytics | Enzo Farias | 163 | 2023-07-15 | 2023-07-15 | 2023-07-01 | 14 | 2023-07-15 | 2023-07-01 | 26 | 2023-07-15 | Teste Analytics/Sprint 13 | 2023-07-01 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4226 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 186 | 2023-07-30 | 2023-07-30 | 2023-07-16 | 14 | 2023-07-30 | 2023-07-16 | 12 | 2023-07-30 | Dev. Analytics/Sprint 14 | 2023-07-16 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4227 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 200 | 2023-09-19 | 2023-09-19 | 2023-07-16 | 65 | 2023-07-30 | 2023-07-16 | 11 | 2023-07-30 | Análise de Requisitos/Sprint 14 | 2023-07-16 | 65 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4228 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 69 | 2023-08-14 | 2023-08-14 | 2023-07-31 | 14 | 2023-08-14 | 2023-07-31 | 38 | 2023-08-14 | Dev. Analytics/Sprint 15 | 2023-07-31 | 14 | 1 - Alta | Projeto 3 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4229 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 109 | 2023-08-29 | 2023-08-29 | 2023-08-15 | 14 | 2023-08-29 | 2023-08-15 | 30 | 2023-08-29 | Análise de Requisitos/Sprint 16 | 2023-08-15 | 14 | 1 - Alta | Projeto 2 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4230 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 28 | 2023-08-29 | 2023-08-29 | 2023-08-15 | 14 | 2023-08-29 | 2023-08-15 | 37 | 2023-08-29 | Dev. Analytics/Sprint 16 | 2023-08-15 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4231 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 145 | 2023-10-06 | 2023-10-06 | 2023-08-30 | 37 | 2023-09-13 | 2023-08-30 | 22 | 2023-09-13 | Teste Analytics/Sprint 17 | 2023-08-30 | 37 | 2 - Média | Projeto 1 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4232 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 115 | 2023-10-22 | 2023-10-22 | 2023-08-30 | 53 | 2023-09-13 | 2023-08-30 | 32 | 2023-09-13 | Análise de Requisitos/Sprint 17 | 2023-08-30 | 53 | 2 - Média | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4233 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 105 | 2023-11-01 | 2023-11-01 | 2023-09-14 | 48 | 2023-09-28 | 2023-09-14 | 27 | 2023-09-28 | Análise de Requisitos/Sprint 18 | 2023-09-14 | 48 | 2 - Média | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4234 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 167 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 28 | 2023-09-28 | Teste Analytics/Sprint 18 | 2023-09-14 | 14 | 2 - Média | Projeto 2 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4235 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 180 | 2023-09-28 | 2023-09-28 | 2023-09-14 | 14 | 2023-09-28 | 2023-09-14 | 22 | 2023-09-28 | Dev. Analytics/Sprint 18 | 2023-09-14 | 14 | 3 - Baixa | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4236 | Product Backlog Item
Teste Analytics | Enzo Farias | 165 | 2023-10-13 | 2023-10-13 | 2023-09-29 | 14 | 2023-10-13 | 2023-09-29 | 10 | 2023-10-13 | Teste Analytics/Sprint 19 | 2023-09-29 | 14 | 1 - Alta | Projeto 3 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4237 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 151 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 11 | 2023-10-28 | Teste Analytics/Sprint 20 | 2023-10-14 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4238 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 112 | 2023-10-28 | 2023-10-28 | 2023-10-14 | 14 | 2023-10-28 | 2023-10-14 | 21 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 14 | 3 - Baixa | Projeto 1 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4239 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 179 | 2023-12-10 | 2023-12-10 | 2023-10-14 | 57 | 2023-10-28 | 2023-10-14 | 36 | 2023-10-28 | Análise de Requisitos/Sprint 20 | 2023-10-14 | 57 | 3 - Baixa | Projeto 2 | Projeto3 |  | Laboratório de dados 2 | Business | 1.0 | 4240 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 192 | 2023-11-12 | 2023-11-12 | 2023-10-29 | 14 | 2023-11-12 | 2023-10-29 | 26 | 2023-11-12 | Análise de Requisitos/Sprint 21 | 2023-10-29 | 14 | 2 - Média | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4241 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 79 | 2023-11-27 | 2023-11-27 | 2023-11-13 | 14 | 2023-11-27 | 2023-11-13 | 12 | 2023-11-27 | Análise de Requisitos/Sprint 22 | 2023-11-13 | 14 | 2 - Média | Projeto 3 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4242 | Product Backlog Item
Dev. Analytics | Enzo Farias | 178 | 2023-11-27 | 2023-11-27 | 2023-11-13 | 14 | 2023-11-27 | 2023-11-13 | 15 | 2023-11-27 | Dev. Analytics/Sprint 22 | 2023-11-13 | 14 | 2 - Média | Projeto 3 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4243 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 125 | 2023-12-31 | 2023-12-31 | 2023-11-13 | 48 | 2023-11-27 | 2023-11-13 | 28 | 2023-11-27 | Dev. Analytics/Sprint 22 | 2023-11-13 | 48 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4244 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 156 | 2023-12-12 | 2023-12-12 | 2023-11-28 | 14 | 2023-12-12 | 2023-11-28 | 26 | 2023-12-12 | Análise de Requisitos/Sprint 23 | 2023-11-28 | 14 | 1 - Alta | Projeto 1 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4245 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 48 | 2023-12-12 | 2023-12-12 | 2023-11-28 | 14 | 2023-12-12 | 2023-11-28 | 34 | 2023-12-12 | Teste Analytics/Sprint 23 | 2023-11-28 | 14 | 1 - Alta | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4246 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 56 | 2024-02-06 | 2024-02-06 | 2023-12-13 | 55 | 2023-12-27 | 2023-12-13 | 8 | 2023-12-27 | Dev. Analytics/Sprint 24 | 2023-12-13 | 55 | 2 - Média | Projeto 3 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4247 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 94 | 2023-12-27 | 2023-12-27 | 2023-12-13 | 14 | 2023-12-27 | 2023-12-13 | 20 | 2023-12-27 | Análise de Requisitos/Sprint 24 | 2023-12-13 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4248 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 174 | 2024-01-11 | 2024-01-11 | 2023-12-28 | 14 | 2024-01-11 | 2023-12-28 | 35 | 2024-01-11 | Análise de Requisitos/Sprint 25 | 2023-12-28 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4249 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 152 | 2024-01-11 | 2024-01-11 | 2023-12-28 | 14 | 2024-01-11 | 2023-12-28 | 23 | 2024-01-11 | Análise de Requisitos/Sprint 25 | 2023-12-28 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4250 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 143 | 2024-01-11 | 2024-01-11 | 2023-12-28 | 14 | 2024-01-11 | 2023-12-28 | 17 | 2024-01-11 | Dev. Analytics/Sprint 25 | 2023-12-28 | 14 | 3 - Baixa | Projeto 3 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4251 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 53 | 2024-01-26 | 2024-01-26 | 2024-01-12 | 14 | 2024-01-26 | 2024-01-12 | 29 | 2024-01-26 | Análise de Requisitos/Sprint 26 | 2024-01-12 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4252 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 129 | 2024-02-26 | 2024-02-26 | 2024-01-27 | 30 | 2024-02-10 | 2024-01-27 | 21 | 2024-02-10 | Dev. Analytics/Sprint 27 | 2024-01-27 | 30 | 3 - Baixa | Projeto 1 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4253 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 26 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 19 | 2024-02-25 | Análise de Requisitos/Sprint 28 | 2024-02-11 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4254 | Product Backlog Item
Teste Analytics | Enzo Farias | 108 | 2024-04-02 | 2024-04-02 | 2024-02-11 | 51 | 2024-02-25 | 2024-02-11 | 10 | 2024-02-25 | Teste Analytics/Sprint 28 | 2024-02-11 | 51 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4255 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 108 | 2024-02-25 | 2024-02-25 | 2024-02-11 | 14 | 2024-02-25 | 2024-02-11 | 36 | 2024-02-25 | Análise de Requisitos/Sprint 28 | 2024-02-11 | 14 | 2 - Média | Projeto 3 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4256 | Product Backlog Item
Teste Analytics | Ísis Monteiro | 128 | 2024-04-06 | 2024-04-06 | 2024-02-26 | 40 | 2024-03-11 | 2024-02-26 | 15 | 2024-03-11 | Teste Analytics/Sprint 29 | 2024-02-26 | 40 | 1 - Alta | Projeto 1 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4257 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 20 | 2024-03-11 | 2024-03-11 | 2024-02-26 | 14 | 2024-03-11 | 2024-02-26 | 16 | 2024-03-11 | Dev. Analytics/Sprint 29 | 2024-02-26 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4258 | Product Backlog Item
Dev. Analytics | Enzo Farias | 49 | 2024-05-05 | 2024-05-05 | 2024-02-26 | 69 | 2024-03-11 | 2024-02-26 | 23 | 2024-03-11 | Dev. Analytics/Sprint 29 | 2024-02-26 | 69 | 2 - Média | Projeto 3 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4259 | Product Backlog Item
Dev. Analytics | Enzo Farias | 148 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 21 | 2024-03-26 | Dev. Analytics/Sprint 30 | 2024-03-12 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4260 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 78 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 20 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 3 - Baixa | Projeto 3 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4261 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 145 | 2024-03-26 | 2024-03-26 | 2024-03-12 | 14 | 2024-03-26 | 2024-03-12 | 25 | 2024-03-26 | Análise de Requisitos/Sprint 30 | 2024-03-12 | 14 | 1 - Alta | Projeto 3 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4262 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 128 | 2024-04-10 | 2024-04-10 | 2024-03-27 | 14 | 2024-04-10 | 2024-03-27 | 9 | 2024-04-10 | Análise de Requisitos/Sprint 31 | 2024-03-27 | 14 | 1 - Alta | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4263 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 170 | 2024-04-30 | 2024-04-30 | 2024-03-27 | 34 | 2024-04-10 | 2024-03-27 | 24 | 2024-04-10 | Dev. Analytics/Sprint 31 | 2024-03-27 | 34 | 4 - Sem Prioridade | Projeto 3 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4264 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 140 | 2024-04-25 | 2024-04-25 | 2024-04-11 | 14 | 2024-04-25 | 2024-04-11 | 19 | 2024-04-25 | Análise de Requisitos/Sprint 32 | 2024-04-11 | 14 | 2 - Média | Projeto 1 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4265 | Product Backlog Item
Dev. Analytics | Enzo Farias | 66 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 11 | 2024-05-10 | Dev. Analytics/Sprint 33 | 2024-04-26 | 14 | 2 - Média | Projeto 3 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4266 | Product Backlog Item
Teste Analytics | Bárbara Andrade | 126 | 2024-07-08 | 2024-07-08 | 2024-04-26 | 73 | 2024-05-10 | 2024-04-26 | 26 | 2024-05-10 | Teste Analytics/Sprint 33 | 2024-04-26 | 73 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4267 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 50 | 2024-05-10 | 2024-05-10 | 2024-04-26 | 14 | 2024-05-10 | 2024-04-26 | 10 | 2024-05-10 | Teste Analytics/Sprint 33 | 2024-04-26 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4268 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 47 | 2024-06-17 | 2024-06-17 | 2024-05-11 | 37 | 2024-05-25 | 2024-05-11 | 35 | 2024-05-25 | Análise de Requisitos/Sprint 34 | 2024-05-11 | 37 | 2 - Média | Projeto 3 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4269 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 56 | 2024-06-30 | 2024-06-30 | 2024-05-11 | 50 | 2024-05-25 | 2024-05-11 | 31 | 2024-05-25 | Teste Analytics/Sprint 34 | 2024-05-11 | 50 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4270 | Product Backlog Item
Análise de Requisitos | Bárbara Andrade | 99 | 2024-05-25 | 2024-05-25 | 2024-05-11 | 14 | 2024-05-25 | 2024-05-11 | 17 | 2024-05-25 | Análise de Requisitos/Sprint 34 | 2024-05-11 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4271 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 37 | 2024-07-12 | 2024-07-12 | 2024-05-26 | 47 | 2024-06-09 | 2024-05-26 | 26 | 2024-06-09 | Análise de Requisitos/Sprint 35 | 2024-05-26 | 47 | 3 - Baixa | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4272 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 120 | 2024-06-09 | 2024-06-09 | 2024-05-26 | 14 | 2024-06-09 | 2024-05-26 | 19 | 2024-06-09 | Análise de Requisitos/Sprint 35 | 2024-05-26 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4273 | Product Backlog Item
Dev. Analytics | Pietro Cassiano | 131 | 2024-06-09 | 2024-06-09 | 2024-05-26 | 14 | 2024-06-09 | 2024-05-26 | 12 | 2024-06-09 | Dev. Analytics/Sprint 35 | 2024-05-26 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4274 | Product Backlog Item
Teste Analytics | Enzo Farias | 56 | 2024-08-14 | 2024-08-14 | 2024-06-10 | 65 | 2024-06-24 | 2024-06-10 | 38 | 2024-06-24 | Teste Analytics/Sprint 36 | 2024-06-10 | 65 | 3 - Baixa | Projeto 2 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4275 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 50 | 2024-06-24 | 2024-06-24 | 2024-06-10 | 14 | 2024-06-24 | 2024-06-10 | 19 | 2024-06-24 | Teste Analytics/Sprint 36 | 2024-06-10 | 14 | 2 - Média | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4276 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 36 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 25 | 2024-07-09 | Dev. Analytics/Sprint 37 | 2024-06-25 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4277 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 116 | 2024-07-28 | 2024-07-28 | 2024-06-25 | 33 | 2024-07-09 | 2024-06-25 | 10 | 2024-07-09 | Dev. Analytics/Sprint 37 | 2024-06-25 | 33 | 4 - Sem Prioridade | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4278 | Product Backlog Item
Análise de Requisitos | Ísis Monteiro | 76 | 2024-07-09 | 2024-07-09 | 2024-06-25 | 14 | 2024-07-09 | 2024-06-25 | 28 | 2024-07-09 | Análise de Requisitos/Sprint 37 | 2024-06-25 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4279 | Product Backlog Item
Teste Analytics | Enzo Farias | 23 | 2024-07-24 | 2024-07-24 | 2024-07-10 | 14 | 2024-07-24 | 2024-07-10 | 37 | 2024-07-24 | Teste Analytics/Sprint 38 | 2024-07-10 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4280 | Product Backlog Item
Dev. Analytics | Enzo Farias | 48 | 2024-07-24 | 2024-07-24 | 2024-07-10 | 14 | 2024-07-24 | 2024-07-10 | 29 | 2024-07-24 | Dev. Analytics/Sprint 38 | 2024-07-10 | 14 | 1 - Alta | Projeto 1 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4281 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 50 | 2024-09-03 | 2024-09-03 | 2024-07-25 | 40 | 2024-08-08 | 2024-07-25 | 23 | 2024-08-08 | Análise de Requisitos/Sprint 39 | 2024-07-25 | 40 | 4 - Sem Prioridade | Projeto 2 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4282 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 173 | 2024-08-23 | 2024-08-23 | 2024-08-09 | 14 | 2024-08-23 | 2024-08-09 | 40 | 2024-08-23 | Dev. Analytics/Sprint 40 | 2024-08-09 | 14 | 1 - Alta | Projeto 1 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4283 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 190 | 2024-09-07 | 2024-09-07 | 2024-08-24 | 14 | 2024-09-07 | 2024-08-24 | 29 | 2024-09-07 | Análise de Requisitos/Sprint 41 | 2024-08-24 | 14 | 3 - Baixa | Projeto 2 | Projeto3 |  | Laboratório de dados 3 | Business | 1.0 | 4284 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 30 | 2024-09-07 | 2024-09-07 | 2024-08-24 | 14 | 2024-09-07 | 2024-08-24 | 25 | 2024-09-07 | Análise de Requisitos/Sprint 41 | 2024-08-24 | 14 | 1 - Alta | Projeto 2 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4285 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 52 | 2024-09-07 | 2024-09-07 | 2024-08-24 | 14 | 2024-09-07 | 2024-08-24 | 13 | 2024-09-07 | Dev. Analytics/Sprint 41 | 2024-08-24 | 14 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4286 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 151 | 2024-09-22 | 2024-09-22 | 2024-09-08 | 14 | 2024-09-22 | 2024-09-08 | 34 | 2024-09-22 | Dev. Analytics/Sprint 42 | 2024-09-08 | 14 | 4 - Sem Prioridade | Projeto 3 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4287 | Product Backlog Item
Teste Analytics | Enzo Farias | 34 | 2024-11-14 | 2024-11-14 | 2024-09-08 | 67 | 2024-09-22 | 2024-09-08 | 16 | 2024-09-22 | Teste Analytics/Sprint 42 | 2024-09-08 | 67 | 1 - Alta | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4288 | Product Backlog Item
Dev. Analytics | Enzo Farias | 68 | 2024-11-02 | 2024-11-02 | 2024-09-23 | 40 | 2024-10-07 | 2024-09-23 | 37 | 2024-10-07 | Dev. Analytics/Sprint 43 | 2024-09-23 | 40 | 1 - Alta | Projeto 3 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4289 | Product Backlog Item
Teste Analytics | Ana Nogueira | 126 | 2024-12-08 | 2024-12-08 | 2024-10-08 | 61 | 2024-10-22 | 2024-10-08 | 33 | 2024-10-22 | Teste Analytics/Sprint 44 | 2024-10-08 | 61 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4290 | Product Backlog Item
Teste Analytics | Pietro Cassiano | 90 | 2024-10-22 | 2024-10-22 | 2024-10-08 | 14 | 2024-10-22 | 2024-10-08 | 20 | 2024-10-22 | Teste Analytics/Sprint 44 | 2024-10-08 | 14 | 4 - Sem Prioridade | Projeto 1 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4291 | Product Backlog Item
Teste Analytics | Ana Nogueira | 98 | 2024-10-22 | 2024-10-22 | 2024-10-08 | 14 | 2024-10-22 | 2024-10-08 | 9 | 2024-10-22 | Teste Analytics/Sprint 44 | 2024-10-08 | 14 | 1 - Alta | Projeto 1 | Projeto2 |  | Laboratório de dados 3 | Business | 1.0 | 4292 | Product Backlog Item
Análise de Requisitos | Ana Nogueira | 111 | 2024-11-06 | 2024-11-06 | 2024-10-23 | 14 | 2024-11-06 | 2024-10-23 | 37 | 2024-11-06 | Análise de Requisitos/Sprint 45 | 2024-10-23 | 14 | 2 - Média | Projeto 1 | Projeto3 |  | Laboratório de dados 1 | Business | 1.0 | 4293 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 102 | 2024-12-31 | 2024-12-31 | 2024-11-07 | 54 | 2024-11-21 | 2024-11-07 | 33 | 2024-11-21 | Dev. Analytics/Sprint 46 | 2024-11-07 | 54 | 1 - Alta | Projeto 1 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4294 | Product Backlog Item
Dev. Analytics | Enzo Farias | 193 | 2024-11-21 | 2024-11-21 | 2024-11-07 | 14 | 2024-11-21 | 2024-11-07 | 25 | 2024-11-21 | Dev. Analytics/Sprint 46 | 2024-11-07 | 14 | 1 - Alta | Projeto 3 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4295 | Product Backlog Item
Dev. Analytics | Bárbara Andrade | 192 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 28 | 2024-12-06 | Dev. Analytics/Sprint 47 | 2024-11-22 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4296 | Product Backlog Item
Dev. Analytics | Ana Nogueira | 177 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 36 | 2024-12-06 | Dev. Analytics/Sprint 47 | 2024-11-22 | 14 | 2 - Média | Projeto 1 | Projeto1 |  | Laboratório de dados 1 | Business | 1.0 | 4297 | Product Backlog Item
Análise de Requisitos | Enzo Farias | 175 | 2024-12-06 | 2024-12-06 | 2024-11-22 | 14 | 2024-12-06 | 2024-11-22 | 26 | 2024-12-06 | Análise de Requisitos/Sprint 47 | 2024-11-22 | 14 | 3 - Baixa | Projeto 1 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4298 | Product Backlog Item
Dev. Analytics | Ísis Monteiro | 47 | 2024-12-21 | 2024-12-21 | 2024-12-07 | 14 | 2024-12-21 | 2024-12-07 | 23 | 2024-12-21 | Dev. Analytics/Sprint 48 | 2024-12-07 | 14 | 2 - Média | Projeto 2 | Projeto1 |  | Laboratório de dados 3 | Business | 1.0 | 4299 | Product Backlog Item
Teste Analytics | Enzo Farias | 28 | 2024-12-21 | 2024-12-21 | 2024-12-07 | 14 | 2024-12-21 | 2024-12-07 | 9 | 2024-12-21 | Teste Analytics/Sprint 48 | 2024-12-07 | 14 | 4 - Sem Prioridade | Projeto 2 | Projeto2 |  | Laboratório de dados 1 | Business | 1.0 | 4300 | Product Backlog Item
Análise de Requisitos | Pietro Cassiano | 114 | 2025-01-14 | 2025-01-14 | 2024-12-07 | 38 | 2024-12-21 | 2024-12-07 | 20 | 2024-12-21 | Análise de Requisitos/Sprint 48 | 2024-12-07 | 38 | 2 - Média | Projeto 1 | Projeto2 |  | Laboratório de dados 2 | Business | 1.0 | 4301 | Product Backlog Item
Teste Analytics | Enzo Farias | 166 | 2025-02-25 | 2025-02-25 | 2024-12-22 | 65 | 2025-01-05 | 2024-12-22 | 36 | 2025-01-05 | Teste Analytics/Sprint 49 | 2024-12-22 | 65 | 4 - Sem Prioridade | Projeto 2 | Projeto1 |  | Laboratório de dados 2 | Business | 1.0 | 4302 | Product Backlog Item